## Tabelle1
[11 empty] | Count | % | Result | Description
[11 empty] | 210 | 100% | Passed | Passed Test |  |  | Pending
Project | Unit Testing of TS1 Library | [9 empty] | 0 | 0% | Failed | Failed Test |  |  | Completed
Owner/done by | Sooraj Sunil (DC-AT/ESP1) | [9 empty] | 0 | 0% | Trivial | Failed Test but issue is not important
TS1 Library Unit Testing
MTPro | [5 empty] | Visual Components |  |  |  | Test No. | Execution |  | Result | Comments | General Comments | Solution Approach | Status
Component | Variant | Property | Data type | Limitation | Default | Component | Variant | Property | Default |  | Start | End
Belt Section | BS 1 | ConveyorLength | Integer | 250 -5000mm | 1000 mm | Belt Section | BS 1 | ConveyorLength | 1000 mm | 1 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorWidth | Integer | 80,120,160 mm | 120 mm |  |  | ConveyorWidth | 120 mm | 2 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 3 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 4 | 23/10/24 | 23/10/24 | Passed | • There are 2 speeds present in component properties |  |  | Completed
|  | StandardSizes | String | Standard Size/Individual Size | Standard Size |  |  | StandardSizes | preserve | 5 | 23/10/24 | 23/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 6 | 23/10/24 | 23/10/24 | Passed
|  | BeltSectionType | String | BS 1, BS 1/M, BS 1/T, BS 1/S | BS 1 |  |  | BeltSectionType | BS 1 | 7 | 23/10/24 | 23/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 8 | 23/10/24 | 23/10/24 | Passed | Disconnect property |  |  | Completed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 9 | 23/10/24 | 23/10/24 | Passed
|  | Motor arrangement | String | Left, Right | Left |  |  | Motor arrangement | Left | 10 | 23/10/24 | 23/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 11 | 23/10/24 | 23/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 12 | 23/10/24 | 23/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 13 | 23/10/24 | 23/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 14 | 23/10/24 | 23/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 15 | 23/10/24 | 23/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 16 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 17 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 18 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 19 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 20 | 23/10/24 | 23/10/24 | Passed
Belt Section | BS 1/M | ConveyorLength | Integer | 300 -5000mm | 1000 mm | Belt Section | BS 1/M | ConveyorLength | 1000 mm | 21 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorWidth | Integer | 80,120,160 mm | 120 mm |  |  | ConveyorWidth | 120 mm | 22 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 23 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 24 | 23/10/24 | 23/10/24 | Passed
|  | StandardSizes | String | Standard Size/Individual Size | Standard Size |  |  | StandardSizes | preserve | 25 | 23/10/24 | 23/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 26 | 23/10/24 | 23/10/24 | Passed
|  | BeltSectionType | String | BS 1, BS 1/M, BS 1/T, BS 1/S | BS 1/M |  |  | BeltSectionType | BS 1/M | 27 | 23/10/24 | 23/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 28 | 23/10/24 | 23/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 29 | 23/10/24 | 23/10/24 | Passed
|  | Motor arrangement | String | Left, Right | Left |  |  | Motor arrangement | Left | 30 | 23/10/24 | 23/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 31 | 23/10/24 | 23/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 32 | 23/10/24 | 23/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 33 | 23/10/24 | 23/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 34 | 23/10/24 | 23/10/24 | Passed
|  | MotorPosition | Integer | 90 - (ConveyorLength-200) | 90 mm |  |  | MotorPosition | preserve | 35 | 23/10/24 | 23/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 36 | 23/10/24 | 23/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 37 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 38 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 39 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 40 | 23/10/24 | 23/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 41 | 23/10/24 | 23/10/24 | Passed
Belt Section | BS 1/T | ConveyorLength | Integer | 320 -5000mm | 1000 mm | Belt Section | BS 1/T | ConveyorLength | 1000 mm | 42 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorWidth | Integer | 80,120,160 mm | 120 mm |  |  | ConveyorWidth | 120 mm | 43 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 44 | 23/10/24 | 23/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 45 | 23/10/24 | 23/10/24 | Passed
|  | StandardSizes | String | Standard Size/Individual Size | Standard Size |  |  | StandardSizes | preserve | 46 | 24/10/24 | 24/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 47 | 24/10/24 | 24/10/24 | Passed
|  | BeltSectionType | String | BS 1, BS 1/M, BS 1/T, BS 1/S | BS 1/T |  |  | BeltSectionType | BS 1/T | 48 | 24/10/24 | 24/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 49 | 24/10/24 | 24/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 50 | 24/10/24 | 24/10/24 | Passed
|  | Motor arrangement | String | Left, Right | Left |  |  | Motor arrangement | Left | 51 | 24/10/24 | 24/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 52 | 24/10/24 | 24/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 53 | 24/10/24 | 24/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 54 | 24/10/24 | 24/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 55 | 24/10/24 | 24/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 56 | 24/10/24 | 24/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 57 | 24/10/24 | 24/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 58 | 24/10/24 | 24/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 59 | 24/10/24 | 24/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 60 | 24/10/24 | 24/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 61 | 24/10/24 | 24/10/24 | Passed
Belt Section | BS 1/S | ConveyorLength | Integer | 520 -5000mm | 1000 mm | Belt Section | BS 1/S | ConveyorLength | 1000 mm | 62 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorWidth | Integer | 80,120,160 mm | 120 mm |  |  | ConveyorWidth | 120 mm | 63 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 64 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 65 | 25/10/24 | 25/10/24 | Passed
|  | StandardSizes | String | Standard Size/Individual Size | Standard Size |  |  | StandardSizes | preserve | 66 | 25/10/24 | 25/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 67 | 25/10/24 | 25/10/24 | Passed
|  | BeltSectionType | String | BS 1, BS 1/M, BS 1/T, BS 1/S | BS 1/S |  |  | BeltSectionType | BS 1/S | 68 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 69 | 25/10/24 | 25/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 70 | 25/10/24 | 25/10/24 | Passed
|  | Motor arrangement | String | Left, Right | Left |  |  | Motor arrangement | Left | 71 | 25/10/24 | 25/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 72 | 25/10/24 | 25/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 73 | 25/10/24 | 25/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 74 | 25/10/24 | 25/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 75 | 25/10/24 | 25/10/24 | Passed
|  | No. Of Segments | Integer | 2,3,4 | 2 |  |  | No. Of Segments | preserve | 76 | 25/10/24 | 25/10/24 | Passed
|  | UniformSectionLength | Boolean | True, False | False |  |  | UniformSectionLength | preserve | 77 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 78 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 79 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 80 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 81 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 82 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 83 | 25/10/24 | 25/10/24 | Passed
Conveyor Unit | With AS1 | ConveyorLength | Integer | 1000 -12400mm | 1000 mm | Conveyor Unit | With AS1 | ConveyorLength | 1000 mm | 84 | 25/10/24 | 25/10/24 | Passed | Lower/Upper limit is incorrect (620-6000mm) |  | Change Conveyor Length UB/LB in modelling | Completed
|  | ConveyorWidth | Integer | 80,120,160 mm | 120 mm |  |  | ConveyorWidth | 120 mm | 85 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 86 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 87 | 25/10/24 | 25/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 88 | 25/10/24 | 25/10/24 | Passed
|  | MaxProfileLength | Integer | 400 -6000mm | 2000 mm |  |  | MaxProfileLength | preserve | 89 | 25/10/24 | 25/10/24 | Passed
|  | Max.distance between CrossConnectors | Integer | 400 -1000mm | 500 mm |  |  | Max.distance between CrossConnectors | preserve | 90 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 91 | 25/10/24 | 25/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 92 | 25/10/24 | 25/10/24 | Passed
|  | Motor arrangement | String | Left, Right | Left |  |  | Motor arrangement | Left | 93 | 25/10/24 | 25/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 94 | 25/10/24 | 25/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 95 | 25/10/24 | 25/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 96 | 25/10/24 | 25/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 97 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 98 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 99 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 100 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 101 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 102 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 103 | 25/10/24 | 25/10/24 | Passed
Drive | AS1 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Drive | AS1 | ConveyorWidth | 120 mm | 104 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 105 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 106 | 25/10/24 | 25/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 107 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 108 | 25/10/24 | 25/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 109 | 25/10/24 | 25/10/24 | Passed
|  | Motor arrangement | String | Left, Right | Left |  |  | Motor arrangement | Left | 110 | 25/10/24 | 25/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 111 | 25/10/24 | 25/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 112 | 25/10/24 | 25/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 113 | 25/10/24 | 25/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 114 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 115 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 116 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 117 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 118 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 119 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 120 | 25/10/24 | 25/10/24 | Passed
Section | ST1 | ConveyorLength | Integer | 200 -6000mm | 1000 mm | Section | ST1 | ConveyorLength | 1000 mm | 121 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorWidth | Integer | 80,120,160 mm | 120 mm |  |  | ConveyorWidth | 120 mm | 122 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 123 | 25/10/24 | 25/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 124 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 125 | 25/10/24 | 25/10/24 | Passed
|  | Max.distance between CrossConnectors | Integer | 400 -1000mm | 500 mm |  |  | Max.distance between CrossConnectors | preserve | 126 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorSpeed | 12 m/min | 127 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 128 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 129 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 130 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 131 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 132 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 133 | 25/10/24 | 25/10/24 | Passed
Return Unit | UM1 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Return Unit | UM1 | ConveyorWidth | 120 mm | 134 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 135 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorSpeed | 12 m/min | 136 | 25/10/24 | 25/10/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | DirectionOfTransport | Forward | 137 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 138 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 139 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 140 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 141 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 142 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 143 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 144 | 25/10/24 | 25/10/24 | Passed
Curves | KU 1/90 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | KU 1/90 | ConveyorWidth | 120 mm | 145 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 146 | 25/10/24 | 25/10/24 | Passed
|  | InfeedSection | Boolean | Yes, No | Yes |  |  | InfeedSection | preserve | 147 | 25/10/24 | 25/10/24 | Passed
|  | OutfeedSection | Boolean | Yes, No | Yes |  |  | OutfeedSection | preserve | 148 | 25/10/24 | 25/10/24 | Passed
|  | InfeedLength L1 | Integer | 150 - 5000mm | 1000 mm |  |  | InfeedLength L1 | preserve | 149 | 25/10/24 | 25/10/24 | Passed
|  | OutfeedLength L2 | Integer | 150 - 5000mm | 1000 mm |  |  | OutfeedLength L2 | preserve | 150 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | CurveType | KU 1/90 | 151 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorDirection | Forward | 152 | 25/10/24 | 25/10/24 | Passed
|  | CurveDirection | String | Left, Right | Left |  |  | CurveDirection | Left | 153 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 154 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 155 | 25/10/24 | 25/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 156 | 25/10/24 | 25/10/24 | Passed
|  | Motor arrangement | String | Outside, Inside | Outside |  |  | Motor arrangement | Outside | 157 | 25/10/24 | 25/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 158 | 25/10/24 | 25/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 159 | 25/10/24 | 25/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 160 | 25/10/24 | 25/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 161 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 162 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 163 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 164 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 165 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 166 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 167 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorAngle | 90 deg | 168 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorRadius | 105 mm | 169 | 25/10/24 | 25/10/24 | Passed
Curves | KE 1/O-90 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | KE 1/O-90 | ConveyorWidth | 120 mm | 170 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 171 | 25/10/24 | 25/10/24 | Passed
|  | CurveDirection | String | Left, Right | Left |  |  | CurveDirection | Left | 172 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | 1 kg | 173 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorSpeed | 12 m/min | 174 | 25/10/24 | 25/10/24 | Passed
|  | Additional drive kit | Boolean | Yes, No | No |  |  | AdditionalDriveKit | False | 175 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | CurveType | KU 1/O-90 | 176 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorDirection | Forward | 177 | 25/10/24 | 25/10/24 | Passed
|  | Installation Location AO | String | Automatic, A, B, C, D | Automatic |  |  | preserve |  | 178 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 179 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 180 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 181 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 182 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 183 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 184 | 25/10/24 | 25/10/24 | Passed
Curves | KU 1/180 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | KU 1/180 | ConveyorWidth | 120 mm | 185 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 186 | 25/10/24 | 25/10/24 | Passed
|  | InfeedSection | Boolean | Yes, No | Yes |  |  | InfeedSection | preserve | 187 | 25/10/24 | 25/10/24 | Passed
|  | OutfeedSection | Boolean | Yes, No | Yes |  |  | OutfeedSection | preserve | 188 | 25/10/24 | 25/10/24 | Passed
|  | InfeedLength L1 | Integer | 150 - 5000mm | 1000 mm |  |  | InfeedLength L1 | preserve | 189 | 25/10/24 | 25/10/24 | Passed
|  | OutfeedLength L2 | Integer | 150 - 5000mm | 1000 mm |  |  | OutfeedLength L2 | preserve | 190 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | CurveType | KU 1/180 | 191 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorDirection | Forward | 192 | 25/10/24 | 25/10/24 | Passed
|  | CurveDirection | String | Left, Right | Left |  |  | CurveDirection | Left | 193 | 25/10/24 | 25/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | preserve | 194 | 25/10/24 | 25/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 m/min |  |  | ConveyorSpeed | 12 m/min | 195 | 25/10/24 | 25/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 196 | 25/10/24 | 25/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 197 | 25/10/24 | 25/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 400 (+10/-12%) |  |  | Voltage | preserve | 198 | 25/10/24 | 25/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 199 | 25/10/24 | 25/10/24 | Passed
|  | MotorMounting | Integer | 0,90,180,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 200 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 201 | 25/10/24 | 25/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 202 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 203 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 204 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 205 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 206 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorAngle | 90 deg | 207 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | ConveyorRadius | 105 mm | 208 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Constant Tx | 145 | 209 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | Constant Ty | 7.5 | 210 | 25/10/24 | 25/10/24 | Passed
Curves | KE 1/O-180 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | KE 1/O-180 | ConveyorWidth | 120 mm | 211 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 212 | 30/10/24 | 30/10/24 | Passed
|  | Distance a | Integer | 60,135 mm | 60 mm |  |  | DistanceA | 60 mm | 213 | 30/10/24 | 30/10/24 | Passed
|  | CurveDirection | String | Left, Right | Left |  |  | CurveDirection | Left | 214 | 30/10/24 | 30/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | 1 kg | 215 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ConveyorSpeed | 12 m/min | 216 | 30/10/24 | 30/10/24 | Passed
|  | Additional drive kit | Boolean | Yes, No | No |  |  | AdditionalDriveKit | False | 217 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | CurveType | KE 1/O-180 | 218 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ConveyorDirection | Forward | 219 | 30/10/24 | 30/10/24 | Passed
|  | Installation Location AO | String | Automatic, A, B, C, D | Automatic |  |  | preserve |  | 220 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 221 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 222 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 223 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 224 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 225 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 226 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | SegmentSize | 0 mm | 227 | 30/10/24 | 30/10/24 | Passed
Curves | CU 1/90 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | CU 1/90 | ConveyorWidth | 120 mm | 228 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 229 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorLength | Integer | 455 - 5000mm (CW120mm) | 455 mm |  |  | ConveyorLength | 1000 mm | 230 | 25/10/24 | 25/10/24 | Passed
|  | CurveDirection | String | Left, Right | Left |  |  | CurveDirection | Left | 231 | 30/10/24 | 30/10/24 | Passed
|  | WTWeight | Real | 0.5 - 3 kg | 1 kg |  |  | WTWeight | 1 kg | 232 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 6 m/min |  |  | ConveyorSpeed | 12 m/min | 233 | 25/10/24 | 25/10/24 | Passed
|  | preserve | [5 empty] | CurveType | CU 1/90 | 234 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ConveyorDirection | Forward | 235 | 30/10/24 | 30/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 236 | 25/10/24 | 25/10/24 | Passed
|  | Motor arrangement | String | Left, Right | Left |  |  | Motor arrangement | Left | 237 | 25/10/24 | 25/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 238 | 25/10/24 | 25/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 200(±10%) |  |  | Voltage | preserve | 239 | 25/10/24 | 25/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 240 | 25/10/24 | 25/10/24 | Passed
|  | MotorMounting | Integer | 0,270 deg | 0 deg |  |  | MotorMounting | 0 deg | 241 | 25/10/24 | 25/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 242 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 243 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 9999 | 244 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 245 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 246 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 247 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | SegmentSize | 0 mm | 248 | 30/10/24 | 30/10/24 | Passed
Leg Sets | SZ 1 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | SZ 1 | ConveyorWidth | 120 mm | 249 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorHeight | Integer | 295 - 2000 mm | 850 mm |  |  | ConveyorHeight | 850 mm | 250 | 30/10/24 | 30/10/24 | Passed
|  | Transport Height, Support H | Integer | 295 - 2000 mm | 850 mm |  |  | Transport Height, Support H | preserve | 251 | 30/10/24 | 30/10/24 | Passed
|  | Reinfrocement | Boolean | Yes, No | No |  |  | Reinfrocement | No | 252 | 30/10/24 | 30/10/24 | Passed
|  | Reinfrocement Height | Integer | 365 - 1937 mm | 365 mm |  |  | Reinfrocement Height | 365 mm | 253 | 30/10/24 | 30/10/24 | Passed
|  | StandardSizes | String | Standard Size/Individual Size | Standard Size |  |  | StandardSizes | preserve | 254 | 30/10/24 | 30/10/24 | Passed
|  | Leg set type | String | SZ1, SZ1/L | SZ1 |  |  | Leg set type | SZ1 | 255 | 30/10/24 | 30/10/24 | Passed
|  | No. Of tracks | Integer | 1,2 | 1 |  |  | No. Of tracks | 1 | 256 | 30/10/24 | 30/10/24 | Passed
|  | AO Location | Real |  | 62.5 |  |  | AO Location | preserve | 257 | 30/10/24 | 30/10/24 | Passed
|  | Foundation bracket | String | Left, Right, Both sides, Without | Left |  |  | Foundation bracket | Left | 258 | 30/10/24 | 30/10/24 | Passed
|  | Assembled | String | Assembled, Not assembled | Not assembled |  |  | Assembled | preserve | 259 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 260 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 261 | 30/10/24 | 30/10/24 | Passed
Leg Sets | SZ 1 /L | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | SZ 1/L | ConveyorWidth | 120 mm | 262 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorHeight | Integer | 280 - 2000 mm | 850 mm |  |  | ConveyorHeight | 850 mm | 263 | 30/10/24 | 30/10/24 | Passed
|  | Transport Height, Support H | Integer | 280 - 2000 mm | 850 mm |  |  | Transport Height, Support H | 850 mm | 264 | 30/10/24 | 30/10/24 | Passed
|  | Reinfrocement | Boolean | Yes, No | No |  |  | Reinfrocement | No | 265 | 30/10/24 | 30/10/24 | Passed
|  | Reinfrocement Height | Integer | 365 - 1937 mm | 365 mm |  |  | Reinfrocement Height | 365 mm | 266 | 30/10/24 | 30/10/24 | Passed
|  | StandardSizes | String | Standard Size/Individual Size | Standard Size |  |  | StandardSizes | preserve | 267 | 30/10/24 | 30/10/24 | Passed
|  | Leg set type | String | 20 | SZ1 |  |  | Leg set type | SZ 1/L | 268 | 30/10/24 | 30/10/24 | Passed
|  | No. Of tracks | Integer |  | 1 |  |  | No. Of tracks | preserve | 269 | 30/10/24 | 30/10/24 | Passed
|  | AO Location | Real |  | 62.5 |  |  | AO Location | preserve | 270 | 30/10/24 | 30/10/24 | Passed
|  | Foundation bracket | String | Left, Right, Both sides, Without | Left |  |  | Foundation bracket | Left | 271 | 30/10/24 | 30/10/24 | Passed
|  | Assembled | String | Assembled, Not assembled | Not assembled |  |  | Assembled | preserve | 272 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 273 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 274 | 30/10/24 | 30/10/24 | Passed
Leg Sets | SZ 1 Two tracks | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Curves | SZ 1 | ConveyorWidth | 120 mm | 275 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorHeight | Integer | 280 - 2000 mm | 850 mm |  |  | ConveyorHeight | 850 mm | 276 | 30/10/24 | 30/10/24 | Passed
|  | Track Spacing | Integer | 60,135 mm | 60 mm |  |  | DistanceA | 60 mm | 277 | 30/10/24 | 30/10/24 | Passed
|  | Transport Height, Support H | Integer | Left, Right | Left |  |  | Transport Height, Support H | Left | 278 | 30/10/24 | 30/10/24 | Passed
|  | Reinfrocement | Boolean | Yes, No | No |  |  | Reinfrocement | No | 279 | 30/10/24 | 30/10/24 | Passed
|  | Reinfrocement Height | Integer | 365 - 1937 mm | 365 mm |  |  | Reinfrocement Height | 365 mm | 280 | 30/10/24 | 30/10/24 | Passed
|  | StandardSizes | String | Standard Size/Individual Size | Standard Size |  |  | StandardSizes | preserve | 281 | 30/10/24 | 30/10/24 | Passed
|  | Leg set type | String | 20 | SZ1 |  |  | Leg set type | SZ1 | 282 | 30/10/24 | 30/10/24 | Passed
|  | No. Of tracks | Integer | 1,2 | 2 |  |  | No. Of tracks | 2 | 283 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | TrackDirection | Same | 284 | 30/10/24 | 30/10/24 | Passed
|  | AO Location | Real |  | 62.5 |  |  | AO Location | preserve | 285 | 30/10/24 | 30/10/24 | Passed
|  | Foundation bracket | String | Left, Right, Both sides, Without | Left |  |  | Foundation bracket | Left | 286 | 30/10/24 | 30/10/24 | Passed
|  | Assembled | String | Assembled, Not assembled | Not assembled |  |  | Assembled | preserve | 287 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 288 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 289 | 30/10/24 | 30/10/24 | Passed
Workpiece Pallet | WT 1/K | WorkPiecePalletSize | Integer | 80,120,160 mm | 120 mm | Workpiece Pallet | WT 1/K | WorkPiecePalletSize | 120 mm | 290 | 30/10/24 | 30/10/24 | Passed
|  | WorkPiecePallet type | String | WT 1/K, WT 1/S, WT 1/P | WT 1/K |  |  | WorkPiecePalletSize | WT 1/K | 291 | 30/10/24 | 30/10/24 | Passed
|  | DampingElementsPosition2-3 | Boolean | Yes, No | No |  |  | DampingElementsPosition2-3 | No | 292 | 30/10/24 | 30/10/24 | Passed
|  | DampingElementsPosition3-4 | Boolean | Yes, No | No |  |  | DampingElementsPosition3-4 | No | 293 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition1 | Boolean | Yes, No | No |  |  | SwitchingElementsPosition1 | No | 294 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition2 | Boolean | Yes, No | Yes |  |  | SwitchingElementsPosition2 | Yes | 295 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition3 | Boolean | Yes, No | No |  |  | SwitchingElementsPosition3 | No | 296 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition4 | Boolean | Yes, No | Yes |  |  | SwitchingElementsPosition4 | Yes | 297 | 30/10/24 | 30/10/24 | Passed
|  | ID system | String | Without, ID 15, ID 200 | Without |  |  | ID system | preserve | 298 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 299 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 300 | 30/10/24 | 30/10/24 | Passed
Workpiece Pallet | WT 1/S | WorkPiecePalletSize | Integer | 80,120,160 mm | 120 mm | Workpiece Pallet | WT 1/S | WorkPiecePalletSize | 120 mm | 301 | 30/10/24 | 30/10/24 | Passed
|  | WorkPiecePallet type | String | WT 1/K, WT 1/S, WT 1/P | WT 1/K |  |  | WorkPiecePalletSize | WT 1/K | 302 | 30/10/24 | 30/10/24 | Passed
|  | DampingElementsPosition2-3 | Boolean | Yes, No | No |  |  | DampingElementsPosition2-3 | No | 303 | 30/10/24 | 30/10/24 | Passed
|  | DampingElementsPosition3-4 | Boolean | Yes, No | No |  |  | DampingElementsPosition3-4 | No | 304 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition1 | Boolean | Yes, No | No |  |  | SwitchingElementsPosition1 | No | 305 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition2 | Boolean | Yes, No | Yes |  |  | SwitchingElementsPosition2 | Yes | 306 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition3 | Boolean | Yes, No | No |  |  | SwitchingElementsPosition3 | No | 307 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition4 | Boolean | Yes, No | Yes |  |  | SwitchingElementsPosition4 | Yes | 308 | 30/10/24 | 30/10/24 | Passed
|  | ID system | String | Without, ID 15, ID 200 | Without |  |  | ID system | preserve | 309 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 310 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 311 | 30/10/24 | 30/10/24 | Passed
Workpiece Pallet | WT 1/P | WorkPiecePalletSize | Integer | 80,120,160 mm | 120 mm | Workpiece Pallet | WT 1/S | WorkPiecePalletSize | 120 mm | 312 | 30/10/24 | 30/10/24 | Passed
|  | WorkPiecePallet type | String | WT 1/K, WT 1/S, WT 1/P | WT 1/K |  |  | WorkPiecePalletSize | WT 1/K | 313 | 30/10/24 | 30/10/24 | Passed
|  | DampingElementsPosition2-3 | Boolean | Yes, No | No |  |  | DampingElementsPosition2-3 | No | 314 | 30/10/24 | 30/10/24 | Passed
|  | DampingElementsPosition3-4 | Boolean | Yes, No | No |  |  | DampingElementsPosition3-4 | No | 315 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition1 | Boolean | Yes, No | No |  |  | SwitchingElementsPosition1 | No | 316 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition2 | Boolean | Yes, No | Yes |  |  | SwitchingElementsPosition2 | Yes | 317 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition3 | Boolean | Yes, No | No |  |  | SwitchingElementsPosition3 | No | 318 | 30/10/24 | 30/10/24 | Passed
|  | SwitchingElementsPosition4 | Boolean | Yes, No | Yes |  |  | SwitchingElementsPosition4 | Yes | 319 | 30/10/24 | 30/10/24 | Passed
|  | ID system | String | Without, ID 15, ID 200 | Without |  |  | ID system | preserve | 320 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 321 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 322 | 30/10/24 | 30/10/24 | Passed
Lift Transverse Unit | HQ 1/U | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Lift Transverse Unit | HQ 1/U | ConveyorWidth | 120 mm | 323 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 324 | 30/10/24 | 30/10/24 | Passed
|  | No. of Lift positions PN | Integer | 2,3 | 2 |  |  | No. of Lift positions PN | preserve | 325 | 30/10/24 | 30/10/24 | Passed
|  | Motor/Gear | String | without Motor/Gear, with Motor without Gear, with Motor/Gear | with Motor/Gear |  |  | Motor/Gear | with Motor/Gear | 326 | 30/10/24 | 30/10/24 | Passed
|  | ConveyorSpeed | Integer | 6,9,12,15,18 | 12 |  |  | ConveyorSpeed | 12 | 327 | 30/10/24 | 30/10/24 | Passed
|  | Frequency | Integer | 50,60 Hz | 50 Hz |  |  | Frequency | preserve | 328 | 30/10/24 | 30/10/24 | Passed
|  | Voltage | Integer | 400 (+10/-12%), 200(±10%) | 200(±10%) |  |  | Voltage | preserve | 329 | 30/10/24 | 30/10/24 | Passed
|  | ConnectionType | String | TerminalBox, CablePlug | TerminalBox |  |  | ConnectionType | preserve | 330 | 30/10/24 | 30/10/24 | Passed
|  | HQ/EQ Application | String | Infeed/Outfeed, Infeed, Outfeed | Infeed/Outfeed |  |  | HQ/EQ Application | preserve | 331 | 30/10/24 | 30/10/24 | Passed
|  | HQ/EQ Lift Position | String | Center, Above, Below | Center |  |  | Lift Position | preserve | 332 | 30/10/24 | 30/10/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 333 | 30/10/24 | 30/10/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 334 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | LiftJoint | 0 | 335 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ShowPortNames | No | 336 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | LiftUp | preserve | 337 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | LiftDown | preserve | 338 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | LiftDelay | 2s | 339 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ControlMode | RoutingRule | 340 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | RuleComponent | Product | 341 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | ConveyorCapacity | 2 | 342 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | Accumulate | True | 343 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | SpaceUtilization | True | 344 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | RetainOffset | True | 345 | 30/10/24 | 30/10/24 | Passed
|  | preserve | [5 empty] | SegmentSize | 0 mm | 346 | 30/10/24 | 30/1024 | Passed
Position Unit | PE 1 | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Position Unit | PE 1 | ConveyorWidth | 120 mm | 347 | 5/11/24 | 5/11/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 348 | 5/11/24 | 5/11/24 | Passed
|  | WT Type | String | WT 1/S and WT 1/K, WT 1/P | WT 1/S and WT 1/K |  |  | WT Type | preserve | 349 | 5/11/24 | 5/11/24 | Passed
|  | Positioning setting | String | Open, Closed | Open |  |  | Positioning setting | preserve | 350 | 5/11/24 | 5/11/24 | Passed
|  | Proximity switch 6.5 x 30 | Boolean | True, False | TRUE |  |  | Proximity switch 6.5 x 30 | TRUE | 351 | 5/11/24 | 5/11/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 352 | 5/11/24 | 5/11/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 353 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Piston | 0 | 354 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ProcessTime | 3 sec | 355 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | PositioningDelay | 2 sec | 356 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ResorceApproach | Right | 357 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ResourceOffset |  | 358 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Capacity | 2 | 359 | 5/11/24 | 5/11/24 | Passed
Lift Position Unit | HP 1/P (h=15) | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Position Unit | HP 1/P (h=15) | ConveyorWidth | 120 mm | 360 | 5/11/24 | 5/11/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 361 | 5/11/24 | 5/11/24 | Passed
|  | PE/HP Type | String | 15mm, 0..5 mm | 15mm |  |  | LiftPositionUnit | HP 1/P (h= 15) | 362 | 5/11/24 | 5/11/24 | Passed
|  | Lift Position | String | Above, Center, Below | Below |  |  | Lift Position | preserve | 363 | 5/11/24 | 5/11/24 | Passed
|  | Dampened Stopper | Boolean | True, False | FALSE |  |  | Dampened Stopper | FALSE | 364 | 5/11/24 | 5/11/24 | Passed
|  | Proximity switch 6.5 x 30 | Boolean | True, False | TRUE |  |  | Proximity switch 6.5 x 30 | TRUE | 365 | 5/11/24 | 5/11/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 366 | 5/11/24 | 5/11/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 367 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Lift | 0 | 368 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ProcessTime | 3 sec | 369 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | LiftDelay | 2 sec | 370 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | PositioningDelay | 0 sec | 371 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ResorceApproach | Right | 372 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ResourceOffset |  | 373 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Capacity | 2 | 374 | 5/11/24 | 5/11/24 | Passed
Lift Position Unit | HP 1/P (h=0..50) | ConveyorWidth | Integer | 80,120,160 mm | 120 mm | Position Unit | HP 1/P (h=0..50) | ConveyorWidth | 120 mm | 375 | 5/11/24 | 5/11/24 | Passed
|  | ConveyorHeight | Integer |  | 850 mm |  |  | ConveyorHeight | 850 mm | 376 | 5/11/24 | 5/11/24 | Passed
|  | PE/HP Type | String | 15mm, 0..5 mm | 15mm |  |  | LiftPositionUnit | HP 1/P (h= 15) | 377 | 5/11/24 | 5/11/24 | Passed
|  | Housing Element | Boolean | True, False | TRUE |  |  | Housing Element | TRUE | 378 | 5/11/24 | 5/11/24 | Passed
|  | Dampened Stopper | Boolean | True, False | FALSE |  |  | Dampened Stopper | FALSE | 379 | 5/11/24 | 5/11/24 | Passed
|  | Proximity switch 6.5 x 30 | Boolean | True, False | TRUE |  |  | Proximity switch 6.5 x 30 | TRUE | 380 | 5/11/24 | 5/11/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 381 | 5/11/24 | 5/11/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 382 | 5/11/24 | 5/11/24 | Passed
|  | LiftPosition | Integer | -25 to 50 mm | 0 mm |  |  | Lift | 0 | 383 | 5/11/24 | 5/11/24 | Passed
|  | MaximumLiftRange | Integer | 0 - 50 mm | 50 mm |  |  | LiftRange | 15 mm | 384 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ProcessTime | 3 sec | 385 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | LiftDelay | 2 sec | 386 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | PositioningDelay | 0 sec | 387 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ResorceApproach | Right | 388 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | ResourceOffset |  | 389 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Capacity | 2 | 390 | 5/11/24 | 5/11/24 | Passed
Stop Gate | VE 1 | preserve |  |  |  | Stop Gate | VE 1 | ConveyorWidth | 120 mm | 391 | 5/11/24 | 5/11/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | Direction | Forward | 392 | 5/11/24 | 5/11/24 | Passed
|  | Stop Gate Type | String | VE 1, VE 1/V | VE 1 |  |  | Type | VE 1 | 393 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Switch | -7 | 394 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Side | Right | 395 | 5/11/24 | 5/11/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 396 | 5/11/24 | 5/11/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 397 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | HighlightTransportationControl |  | 398 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Task | CapacityControl | 399 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | CapacityControlAreaCapacity | 1 | 400 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | CapacityControlCounter | preserve | 401 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | CapacityControlIsMaster | TRUE | 402 | 5/11/24 | 5/11/24 | Passed
Stop Gate | VE 1/V | preserve |  |  |  | Stop Gate | VE 1/V | ConveyorWidth | 120 mm | 403 | 5/11/24 | 5/11/24 | Passed
|  | DirectionOfTransport | String | Forward, Backward,Alternating | Forward |  |  | Direction | Forward | 404 | 5/11/24 | 5/11/24 | Passed
|  | Stop Gate Type | String | VE 1, VE 1/V | VE 1/V |  |  | Type | VE 1/V | 405 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Switch | -7 | 406 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Side | Right | 407 | 5/11/24 | 5/11/24 | Passed
|  | Position | Array(Real)[3] |  |  |  |  | Coordinates (World)[x,y,z] |  | 408 | 5/11/24 | 5/11/24 | Passed
|  | Rotation | Array(Int)[3] |  |  |  |  | Coordinates (World)[Rx,Ry,Rz] |  | 409 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | HighlightTransportationControl |  | 410 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | Task | CapacityControl | 411 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | CapacityControlAreaCapacity | 1 | 412 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | CapacityControlCounter | preserve | 413 | 5/11/24 | 5/11/24 | Passed
|  | preserve | [5 empty] | CapacityControlIsMaster | TRUE | 414 | 5/11/24 | 5/11/24 | Passed
Note on J176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hidden
Note on J177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hidden
Note on J215: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hidden Property
Note on J216: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hidden Property
Note on J217: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hidden Property
Note on J218: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hidden Property